## WBS
Task Group | Task | Assign | From | To | % completed | Note
Project Management | Họp dự án tuần | All | 2020-07-04 09:00 | 2020-07-04 10:00 | 100% | Họp qua MS Team
Project Implementation | Khảo sát yêu cầu | Châu | 15/4/2020 | 16/4/2020 |  | Hẹn gặp trực tiếp khách hàng
Project Management | Họp thống kê lại các yêu cầu | All | 17/4/2020 20:00 | 18/4/2020 21:00 |  | Họp qua MS Team
Training | Trainning: | All | 20/4/2020 | 30/4/2020 |  | Đào tạo ngôn ngữ lập trình chính và các tool phụ
Training | - Ôn lại Javascipt | All | 20/4/2020 | 22/4/2020 |  | Tự ôn lại kiến thức trên mạng hoặc trao đổi với nhau
Training | - Học ngôn ngữ lập trình React.js | All | 23/4/2020 | 28/4/2020 |  | Học trên Youtube và những người quen biết
Training | - Học tool StartUML & thao tác trên Visual Studio Code | All | 29/4/2020 | 30/4/2020 |  | Học trên Youtube và những người quen biết
Project Implementation | Phân tích và thiết kế phần mềm: | All | 2020-01-05 | 2020-07-05 |  | Phân tích phần mềm và phân công
Project Implementation | -Vẽ use case diagram | Sang | 2020-01-05 | 2020-07-05 |  | Tool StartUML
Project Implementation | -Mô hình hóa yêu cầu | Đạt | 2020-01-05 | 2020-07-05 |  | Word, Excel
Project Implementation | -Thiết kế dữ liệu | Đạt | 2020-01-05 | 2020-07-05 |  | Word, Excel
Project Management | Theo dõi và báo cáo tiến bộ | All | 2020-08-05 09:00 | 2020-08-05 10:00 |  | MS team
Project Implementation | Viết code: | All | 2020-09-05 | 30/5/2020 |  | Trong quá trình code có thể bổ sung cho nhau
| -Module Client | Châu | 2020-09-05 | 15/5/2020 |  | Thiết kế giao diện người dùng
| -Module Admin | Đạt | 2020-09-05 | 15/5/2020 |  | Thiết kế giao diện người quản lí
| - BackEnd | Sang | 16/5/2020 | 25/5/2020 |  | Làm bằng React.js
| -Kết nối với cơ sở dữ liệu | All | 26/5/2020 | 30/5/2020 |  | MySQL
Project Management | Theo dõi và báo cáo tiến bộ | All | 31/5/2020 9:00:00 AM | 31/5/2020 9:00:00 AM |  | MS team
Project Implementation | Test sản phẩm lần 1 | All | 2020-01-06 | 2020-02-06 |  | Cả nhóm cùng test sản phẩm
Project Implementation | Trao đổi với khách hàng | Châu | 2020-03-06 | 2020-03-06 |  | Cho khách xem demo và lưu lại ý kiến
Project Implementation | Test sản phẩm lần 2 | All | 2020-04-06 | 15/6/2020 |  | Sửa lại theo yêu cầu của khách
Project Management | Release | All | 16/6/2020 |  |  | Giao sản phẩm cho khách hàng

## Risk Mgmt
No | Risk | Risk Description | Risk Type | Risk Group | Affects | Probability | Exponent | Strategy Type | Strategy Description
1 | Staff turnover | Thành viên trong nhóm bỗng bận làm việc khác hoặc k tham gia đều các buổi họp | People |  | 3 | 25% | 0.75 | Avoid Risk | đề ra hình phạt, nhắc nhở thích đáng cho những ai không tập trung
2 | Hardware unavailability | nhiều thành viên không đáp ứng được trang thiết bị hỗ trợ họp online | Technology |  | 5 | 10% | 0.5 | Plan B | cung cấp video tài liệu đầy đủ cho thành viên không thể tham gia buổi họp, để họ có thể tham khảo và tự làm
3 | CASE tool underperformance | ứng dụng hỗ trợ học online còn xa lạ, ít được dùng | Tool |  | 1 | 25% | 0.25 | Minimize Affects | gửi tài liệu hướng dẫn sử dụng tool
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0

## Ref
Risk group | Mức độ rủi ro | Xác suất rủi ro | Task Group | Risk type | Strategy Type | Member
C1 - Customers & Users | 1 | 10% | Project Management | Technology | Avoid Risk | All
C2 - Scope & requirement | 2 | 25% | CM Management | People | Minimize Affects | Sang
C3 - Execution | 3 | 50% | Training | Organizational | Plan B | Châu
C4 - Environment | 4 | 75% | Project Implementation | Tool |  | Đạt
| 5 | 100% | Package and Release | Requirement
Estimation